## Instructions
How to Use This Gantt Chart Template | For detailed instructions, visit our full guide:
https://www.teamgantt.com/free-gantt-chart-excel-template
📝 Task Table (enter your project details here)
Add each task, phase, or milestone in the Task Table tab.
Fill in Start Date, End Date, % Complete, Assigned To, and Priority.
Columns with formulas update automatically:
✅ Duration = End Date - Start Date + 1
✅ Completed = Duration * % Complete
✅ Remaining = Duration - Completed
Use WBS numbers (1, 1.1, 1.2, etc.) to organize phases and subtasks.
Leave group rows at 0% Complete so they show as dividers without skewing progress.
📊 Gantt Chart (visual project timeline)
The Gantt Chart tab updates automatically as you edit the Task Table.
Task bars display start and end dates; progress shows inside the bars.
Keep phase bars neutral (e.g., gray) and milestones gold for clarity.
📈 Dashboard (project snapshot)
The Dashboard tab shows:
✅ Total project duration
✅ Overall % completion
✅ Days remaining
✅ Task breakdown (not started, in progress, complete)
Metrics update automatically based on the Task Table.
“Not started” excludes group rows for accuracy.
💡 Tips
Use Predecessors to note dependencies (by WBS number).
If the Gantt chart doesn’t print fully:
1. Go to Page Layout → Print Area → Clear Print Area.
2. Reset the print area to include your full chart.

## Dashboard
Project: Spot To Go
Project owner: Nagenthiran Nagarajh
Total project duration | Overall completion | Days remaining
Tasks complete | Tasks in progress | Tasks not started
Note on A4: Formula: =MAX(EndDateColumn) - MIN(StartDateColumn) + 1 (total calendar days across the project)
Note on B4: Formula: =AVERAGE(SelectedTaskPercentCompleteCells) (average % complete across task rows only; group rows are excluded)
Note on C4: Formula: =MAX(0, MAX(EndDateColumn) - TODAY()) (calendar days left until project end; shows 0 if overdue)
Note on A7: Formula: =COUNTIF(PercentCompleteColumn,1) (counts tasks at 100% complete)
Note on B7: Formula: =COUNTIFS(PercentCompleteColumn,">0",PercentCompleteColumn,"<1") (counts tasks with partial progress)
Note on C7: Formula: =SUMPRODUCT(((%CompleteRange=0)+(%CompleteRange="")>0)*(ISNUMBER(SEARCH(".",WBSRange&"")))) (counts tasks at 0% complete or blank; excludes group rows by only counting WBS numbers with decimals)

## Task Table
WBS # | Task Name | Start Date | End Date | Duration | % Complete | Completed | Remaining | Assigned To | Priority | Predecessor
1 | WP1: Literature Review | 2026-04-27 | 2026-05-22
1.1 | Requirements & background analysis | 2026-04-27 | 2026-05-08 |  | 100% |  |  | Nagenthiran Nagarajh | Medium
1.2 | Literature review (4 areas) | 2026-04-27 | 2026-05-15 |  | 100% |  |  | Nagenthiran Nagarajh | Medium
1.3 | Proposal writing & submission | 2026-05-11 | 2026-05-22 |  | 100% |  |  | Nagenthiran Nagarajh | High | 1.2
2 | WP2: Setup & Architecture | 2026-05-04 | 2026-05-29
2.1 | Android Studio project scaffold | 2026-05-04 | 2026-05-15 |  | 100% |  |  | Nagenthiran Nagarajh | Medium
2.2 | Dependency & Gradle configuration | 2026-05-11 | 2026-05-22 |  | 100% |  |  | Nagenthiran Nagarajh | Medium | 2.1
2.3 | API keys & Cloud Console setup | 2026-05-11 | 2026-05-29 |  | 100% |  |  | Nagenthiran Nagarajh | High | 2.1
3 | WP3: Maps & Location | 2026-05-25 | 2026-07-03
3.1 | Google Map integration & GPS centring | 2026-05-25 | 2026-06-12 |  | 100% |  |  | Nagenthiran Nagarajh | Medium
3.2 | Restaurant markers (seed data) | 2026-06-01 | 2026-06-19 |  | 100% |  |  | Nagenthiran Nagarajh | Medium | 3.1
3.3 | Location permission handling | 2026-06-08 | 2026-06-19 |  | 1 |  |  | Nagenthiran Nagarajh | Medium | 3.1
3.4 | Firebase Authentication (login/register) | 2026-06-15 | 2026-07-03 |  | 1 |  |  | Nagenthiran Nagarajh | High | 3.3
4 | WP4: Detail & Video | 2026-06-22 | 2026-07-17
4.1 | Restaurant detail screen | 2026-06-22 | 2026-07-03 |  | 1 |  |  | Nagenthiran Nagarajh | Medium
4.2 | Video screen & YouTube intent | 2026-06-29 | 2026-07-10 |  | 1 |  |  | Nagenthiran Nagarajh | Medium | 4.1
4.3 | Directions screen & Maps intent | 2026-07-06 | 2026-07-17 |  | 1 |  |  | Nagenthiran Nagarajh | Medium | 4.2
5 | WP5: Search & UI Polish | 2026-07-06 | 2026-07-31
5.1 | Keyword search bar | 2026-07-06 | 2026-07-17 |  | 1 |  |  | Nagenthiran Nagarajh | Medium
5.2 | Gemini AI natural-language search | 2026-07-13 | 2026-07-24 |  | 1 |  |  | Nagenthiran Nagarajh | Medium | 5.1
5.3 | Bottom navigation & UI fixes | 2026-07-20 | 2026-07-31 |  | 1 |  |  | Nagenthiran Nagarajh | Medium | 5.2
6 | WP6: Testing & Writing | 2026-07-20 | 2026-08-14
6.1 | Manual functional testing & bug fixes | 2026-07-20 | 2026-08-07 |  | 1 |  |  | Nagenthiran Nagarajh | High
6.2 | Usability heuristic review | 2026-07-27 | 2026-08-07 |  | 1 |  |  | Nagenthiran Nagarajh | Medium | 6.1
6.3 | Final report writing | 2026-07-27 | 2026-08-14 |  | 1 |  |  | Nagenthiran Nagarajh | High | 6.1
7 | WP7: Report & Presentation | 2026-08-10 | 2026-08-21
7.1 | Report review & polish | 2026-08-10 | 2026-08-21 |  | 1 |  |  | Nagenthiran Nagarajh | High
7.2 | Presentation preparation | 2026-08-10 | 2026-08-21 |  | 1 |  |  | Nagenthiran Nagarajh | High
Note on E1: Formula: =End Date - Start Date + 1 (counts both start and end dates)
Note on F1: Note: For group rows, either leave at 0% (simpler, for structure only) or use a weighted average formula to calculate progress across all tasks in the group. Weighted average formula: =SUMPRODUCT(DurationRange, PercentCompleteRange) / SUM(DurationRange)
Note on G1: Formula: =Duration * %Complete (portion of task finished)
Note on H1: Formula: =Duration - Completed (days still left to finish)