## Instructions
How to Use This Gantt Chart Template | For detailed instructions, visit our full guide:
https://www.teamgantt.com/free-gantt-chart-excel-template
📝 Task Table (enter your project details here)
Add each task, phase, or milestone in the Task Table tab.
Fill in Start Date, End Date, % Complete, Assigned To, and Priority.
Columns with formulas update automatically:
✅ Duration = End Date - Start Date + 1
✅ Completed = Duration * % Complete
✅ Remaining = Duration - Completed
Use WBS numbers (1, 1.1, 1.2, etc.) to organize phases and subtasks.
Leave group rows at 0% Complete so they show as dividers without skewing progress.
📊 Gantt Chart (visual project timeline)
The Gantt Chart tab updates automatically as you edit the Task Table.
Task bars display start and end dates; progress shows inside the bars.
Keep phase bars neutral (e.g., gray) and milestones gold for clarity.
📈 Dashboard (project snapshot)
The Dashboard tab shows:
✅ Total project duration
✅ Overall % completion
✅ Days remaining
✅ Task breakdown (not started, in progress, complete)
Metrics update automatically based on the Task Table.
“Not started” excludes group rows for accuracy.
💡 Tips
Use Predecessors to note dependencies (by WBS number).
If the Gantt chart doesn’t print fully:
1. Go to Page Layout → Print Area → Clear Print Area.
2. Reset the print area to include your full chart.

## Dashboard
Project: Acme Web Redesign
Project owner: Emily Sanchez
Total project duration | Overall completion | Days remaining
54 | 31.25% | 172
Tasks complete | Tasks in progress | Tasks not started
1 | 6 | 4
Note on A4: Formula: =MAX(EndDateColumn) - MIN(StartDateColumn) + 1 (total calendar days across the project)
Note on B4: Formula: =AVERAGE(SelectedTaskPercentCompleteCells) (average % complete across task rows only; group rows are excluded)
Note on C4: Formula: =MAX(0, MAX(EndDateColumn) - TODAY()) (calendar days left until project end; shows 0 if overdue)
Note on A7: Formula: =COUNTIF(PercentCompleteColumn,1) (counts tasks at 100% complete)
Note on B7: Formula: =COUNTIFS(PercentCompleteColumn,">0",PercentCompleteColumn,"<1") (counts tasks with partial progress)
Note on C7: Formula: =SUMPRODUCT(((%CompleteRange=0)+(%CompleteRange="")>0)*(ISNUMBER(SEARCH(".",WBSRange&"")))) (counts tasks at 0% complete or blank; excludes group rows by only counting WBS numbers with decimals)

## Task Table
WBS # | Task Name | Start Date | End Date | Duration | % Complete | Completed | Remaining | Assigned To | Priority | Predecessor
1 | Planning Phase | 2026-01-05 | 2026-01-16 | 12 | 75% | 9 | 3
1.1 | Define project goals | 2026-01-05 | 2026-01-09 | 5 | 100% | 5 | 0 | Emily | High
1.2 | Gather requirements | 2026-01-12 | 2026-01-16 | 5 | 50% | 2.5 | 2.5 | Emily | Medium | 1.1
2 | Design Phase | 2026-01-19 | 2026-02-06 | 19 | 14.71% | 2.7941 | 16.2059
2.1 | Create wireframes | 2026-01-19 | 2026-01-23 | 5 | 50% | 2.5 | 2.5 | Kwame | High | 1.2
2.2 | Design mockups | 2026-01-26 | 2026-02-05 | 11 | 0% | 0 | 11 | Sarah | High | 2.1
2.3 | Milestone: Design complete | 2026-02-06 | 2026-02-06 | 1 | 0% | 0 | 1 | — | High | 2.2
3 | Development Phase | 2026-02-09 | 2026-02-27 | 19 | 35.29% | 6.7059 | 12.2941
3.1 | Build website pages | 2026-02-09 | 2026-02-20 | 12 | 50% | 6 | 6 | Charles | High | 2.3
3.2 | Integrate CMS | 2026-02-23 | 2026-02-26 | 4 | 0% | 0 | 4 | Priya | Medium | 3.1
3.3 | Milestone: Launch | 2026-02-27 | 2026-02-27 | 1 | 0% | 0 | 1 | — | High | 3.2
Note on E1: Formula: =End Date - Start Date + 1 (counts both start and end dates)
Note on F1: Note: For group rows, either leave at 0% (simpler, for structure only) or use a weighted average formula to calculate progress across all tasks in the group. Weighted average formula: =SUMPRODUCT(DurationRange, PercentCompleteRange) / SUM(DurationRange)
Note on G1: Formula: =Duration * %Complete (portion of task finished)
Note on H1: Formula: =Duration - Completed (days still left to finish)